## User Acceptance Testing
Want more best practices? Visit www.Praxie.com
User Acceptance Testing, otherwise known as beta testing, is an essential step in the process where a proposed strategy, technology implementation, or product is tested with a group of individuals that are representative of the audience that will be affected by or utilize a new system. These “users” are typically individuals who are employees who volunteer or are requested to try out the new technology or service.
| Project Name: | Psycho Fox
| Client: | Dr. Galloway
| Team: | Matthew, Nicholas, Cy, Harsha
Lead QA/Tester:
| Deadline: | 2023-12-01
| Item # | Acceptance Criteria or Requirement | Test Type | Owner or Responsible | Priority | Test Result | Test Date | Comments
| 1 | Functional: The project should allow the main character to be controlled by the keyboard or gamepad. | Functional | Harsha | HIGH | Pass | 2023-11-26
| 2 | Functional: The project should allow multiple players to create separate accounts. | Functional | Matthew | MEDIUM | Pass | 2023-11-26
| 3 | Functional: The project should implement a login system for users and administrators. | Functional | Cylis | MEDIUM | Pass | 2023-11-26
| 4 | Functional: The project should save the state/progress of all players and allow players to continue once they've logged into their account. | Functional | Nicholas | MEDIUM | Fail | 2023-11-26 | We currently have the login/registration system working but need to finish implementing the save states.
| 5 | Functional: The Project should allow players to lose a life by taking damage or hitting a death barrier. | Functional |  | HIGH | Pass | 2023-11-30
| 6 | Functional: Players should be able to obtain and use items within the game. | Functional |  | MEDIUM | Fail | 2023-11-30 | Due to time constraint, items are not implemented and the player can not obtain or use them.
| 7 | Functional: The enemy objects in the game should have a basic AI and pathfinding to attack the player. | Functional |  | MEDIUM | Pass | 2023-11-30
| 8 | Functional: The game should include obsticals that the player must navigate to complete the level. | Functional |  | HIGH | Pass | 2023-11-30
| 9 | Functional: The Game should include music and audio pertaining to the current scene. | Functional |  | MEDIUM | Pass | 2023-11-30
| 10 | Functional: The project should display a splash screen when launched which also shows top scores and the login prompt. | Functional | Cylis | MEDIUM | Pass | 2023-11-26
| 11 | Nonfunctional: The project should be implemented using the Unity game engine and development environment. | Performance |  | HIGH | Pass | 2023-11-26
| 12 | Nonfunctional: The project team should create a complete replica of the game. | Performance |  | MEDIUM | Pass | 2023-11-26
| 13 | Nonfunctional: The project can use pre-developed images, artwork, audio, and other related media. | Performance |  | MEDIUM | Pass | 2023-11-26
| 14 | Nonfunctional: All project source code must be developed by the CS 360 project team. | Performance |  | HIGH | Pass | 2023-11-26
| 15 | Nonfunctional: The project must use a database. | Performance |  | MEDIUM | Pass | 2023-11-26
| 16 | Nonfunctional: Performance metrics should be gathered and optimized. | Performance |  | MEDIUM | Pass | 2023-11-26
| 17 | Nonfunctional: Security metrics should be gathered and optimized. | Performance |  | MEDIUM | Fail | 2023-11-26 | We will test this once we finish the remaining functionality
| 18 | Nonfunctional: The game should run at a consistent refresh rate. | Performance |  | MEDIUM | Pass | 2023-11-30
| 19 | Nonfunctional: The game should use the correct amount of resources that it is provided. | Performance |  | MEDIUM | Pass | 2023-11-30
| 20 | Nonfunctional: User interface metrics should be gathered and optimized. | Performance |  | MEDIUM | Pass | 2023-11-26
User Acceptance Testing Template